## Cost_Tracking (hidden)
Project_ID | cost_category | sub_category | budgeted_amount | actual_spent | invoice_date | payment_status | supplier_name | variance_pct | payment_due | notes
PRJ001 | Preliminaries | Site Setup | 450000 | 468000 | 4530600% | Paid | SitePrep Ltd | 0.04 | Paid | Additional security requirements
PRJ001 | Preliminaries | Temporary Works | 280000 | 275000 | 4531100% | Paid | TempWorks Co | -0.018 | Paid | Under budget
PRJ001 | Foundation | Excavation | 850000 | 842000 | 4532300% | Paid | DigCo Ltd | -0.009 | Paid | Completed ahead of schedule
PRJ001 | Foundation | Piling | 1200000 | 1245000 | 4533700% | Paid | PilePro UK | 0.038 | Paid | Additional piles required
PRJ001 | Foundation | Waterproofing | 380000 | 385000 | 4534200% | Paid | WaterTech Ltd | 0.013 | Paid | Additional treatment needed
PRJ001 | Structure | Concrete Works | 2800000 | 2650000 | 4535200% | In Process | ConcretePro Ltd | -0.054 | 30/3/2024 | Bulk purchase savings
PRJ001 | Structure | Steel Reinforcement | 1900000 | 2050000 | 4535600% | In Process | SteelCorp UK | 0.079 | 4/4/2024 | Steel price increase
PRJ001 | Structure | Formwork | 950000 | 920000 | 4536100% | In Process | FormTech Ltd | -0.032 | 9/4/2024 | Reuse of forms
PRJ001 | MEP | Electrical | 1850000 | 900000 | 4536600% | In Process | ElectroPro Ltd | N/A | 14/4/2024 | Work in progress
PRJ001 | MEP | Plumbing | 1200000 | 580000 | 4536600% | In Process | PlumbTech UK | N/A | 14/4/2024 | Work in progress
PRJ002 | Preliminaries | Site Setup | 380000 | 375000 | 4534200% | Paid | SitePrep Ltd | -0.013 | Paid | Efficient setup
PRJ002 | Preliminaries | Temporary Works | 250000 | 248000 | 4534700% | Paid | TempWorks Co | -0.008 | Paid | As planned
PRJ002 | Foundation | Excavation | 720000 | 735000 | 4535200% | Paid | DigCo Ltd | 0.021 | Paid | Hard rock encountered
PRJ002 | Foundation | Piling | 980000 | 975000 | 4535600% | Paid | PilePro UK | -0.005 | Paid | As per design
PRJ002 | Structure | Concrete Works | 2400000 | 1200000 | 4536600% | In Process | ConcretePro Ltd | N/A | 14/4/2024 | Work in progress
PRJ002 | Structure | Steel Reinforcement | 1650000 | 850000 | 4536600% | In Process | SteelCorp UK | N/A | 14/4/2024 | Work in progress
PRJ003 | Preliminaries | Site Setup | 320000 | 315000 | 4533700% | Paid | SitePrep Ltd | -0.016 | Paid | Standard setup
PRJ003 | Foundation | Excavation | 580000 | 595000 | 4534700% | Paid | DigCo Ltd | 0.026 | Paid | Additional depth required
PRJ003 | Foundation | Piling | 850000 | 848000 | 4535600% | Paid | PilePro UK | -0.002 | Paid | As designed
PRJ003 | Structure | Concrete Works | 1950000 | 980000 | 4536600% | In Process | ConcretePro Ltd | N/A | 14/4/2024 | Work in progress
PRJ003 | Structure | Steel Reinforcement | 1400000 | 680000 | 4536600% | In Process | SteelCorp UK | N/A | 14/4/2024 | Work in progress
PRJ004 | Preliminaries | Site Setup | 420000 | 425000 | 4530100% | Paid | SitePrep Ltd | 0.012 | Paid | Additional hoarding required
PRJ004 | Preliminaries | Temporary Works | 265000 | 268000 | 4530600% | Paid | TempWorks Co | 0.011 | Paid | Additional temporary support
PRJ004 | Foundation | Excavation | 780000 | 775000 | 4532300% | Paid | DigCo Ltd | -0.006 | Paid | Good ground conditions
PRJ004 | Foundation | Piling | 1100000 | 1095000 | 4533700% | Paid | PilePro UK | -0.005 | Paid | As designed
PRJ004 | Structure | Concrete Works | 2600000 | 1850000 | 4536600% | In Process | ConcretePro Ltd | N/A | 14/4/2024 | Work in progress
PRJ004 | Structure | Steel Reinforcement | 1800000 | 1200000 | 4536600% | In Process | SteelCorp UK | N/A | 14/4/2024 | Work in progress
PRJ005 | Preliminaries | Site Setup | 480000 | 495000 | 4534700% | Paid | SitePrep Ltd | 0.031 | Paid | Site access modifications
PRJ005 | Preliminaries | Temporary Works | 310000 | 308000 | 4535200% | Paid | TempWorks Co | -0.006 | Paid | As planned
PRJ005 | Foundation | Excavation | 920000 | 945000 | 4535600% | Paid | DigCo Ltd | 0.027 | Paid | Underground utilities diversion
PRJ005 | Foundation | Piling | 1350000 | 1320000 | 4536100% | Paid | PilePro UK | -0.022 | Paid | Optimization in pile design
PRJ005 | Structure | Concrete Works | 3100000 | 1200000 | 4536600% | In Process | ConcretePro Ltd | N/A | 14/4/2024 | Work in progress
PRJ005 | Structure | Steel Reinforcement | 2200000 | 850000 | 4536600% | In Process | SteelCorp UK | N/A | 14/4/2024 | Work in progress

## Projects_Timeline (hidden)
Project_ID | Building_Name | Start_Date | Planned_End_Date | Current_Status | Floor_Count | Location
PRJ001 | Azure Heights Tower | 4530600% | 4583800% | In Progress | 32 | London
PRJ002 | Emerald Business Plaza | 4535200% | 4600600% | In Progress | 28 | Manchester
PRJ003 | Sapphire Residences | 4533200% | 4588900% | In Progress | 25 | Birmingham
PRJ004 | Crystal Garden Complex | 4529600% | 4586300% | In Progress | 30 | Leeds
PRJ005 | Riverside Tower | 4534200% | 4591000% | In Progress | 35 | Liverpool

## Project_Resources (hidden)
Project_ID | resource_type | resource_category | allocated_qty | utilized_qty | resource_status | allocation_date | unit_cost | supplier | location_zone | remarks
PRJ001 | Skilled Labor | Concrete Workers | 25 | 22 | Active | 4532300% | 280 | StaffPro Ltd | Foundation | High performance team
PRJ001 | Skilled Labor | Steel Fixers | 15 | 15 | Active | 4532300% | 295 | StaffPro Ltd | Structure | Full capacity utilization
PRJ001 | Skilled Labor | MEP Technicians | 12 | 10 | Active | 4533700% | 310 | TechStaff UK | MEP | 2 on leave
PRJ001 | Skilled Labor | Carpenters | 18 | 15 | Active | 4534200% | 275 | BuildStaff Co | Finishing | Training new staff
PRJ001 | Unskilled Labor | General Workers | 40 | 35 | Active | 4532300% | 180 | WorkForce Inc | All Zones | Regular rotation
PRJ001 | Equipment | Tower Crane | 2 | 2 | Operational | 4532300% | 8500 | CranePro UK | Structure | Monthly maintenance done
PRJ001 | Equipment | Concrete Pumps | 3 | 2 | Operational | 4532300% | 2200 | PumpMaster Ltd | Foundation | One under repair
PRJ001 | Equipment | Excavators | 4 | 3 | Maintenance | 4532300% | 1800 | EarthMovers Ltd | Foundation | Scheduled maintenance
PRJ001 | Equipment | Scaffolding Sets | 15 | 12 | Active | 4533700% | 450 | ScaffoldPro | Structure | Safety checked
PRJ001 | Materials | Concrete (m³) | 850 | 720 | In Stock | 4533700% | 125 | CementEx Ltd | Foundation | Quality tested
PRJ001 | Materials | Rebar (tonnes) | 380 | 290 | In Stock | 4533700% | 980 | SteelCorp UK | Structure | Grade 60
PRJ001 | Safety Equipment | Fall Protection | 85 | 75 | Active | 4532300% | 180 | SafetyFirst Ltd | All Zones | Monthly inspection done
PRJ001 | Special Equipment | BIM Scanner | 1 | 1 | Active | 4536100% | 5500 | TechScan Ltd | All Zones | New equipment
PRJ002 | Skilled Labor | Concrete Workers | 20 | 18 | Active | 4534700% | 280 | StaffPro Ltd | Foundation | Experienced team
PRJ002 | Skilled Labor | Steel Fixers | 12 | 12 | Active | 4534700% | 295 | StaffPro Ltd | Structure | All present
PRJ002 | Skilled Labor | MEP Technicians | 10 | 8 | Active | 4535200% | 310 | TechStaff UK | MEP | Short staffed
PRJ002 | Unskilled Labor | General Workers | 35 | 30 | Active | 4534700% | 180 | WorkForce Inc | All Zones | Need more workers
PRJ002 | Equipment | Tower Crane | 1 | 1 | Operational | 4534700% | 8500 | CranePro UK | Structure | Regular maintenance
PRJ002 | Equipment | Concrete Pumps | 2 | 2 | Operational | 4534700% | 2200 | PumpMaster Ltd | Foundation | Working well
PRJ002 | Materials | Concrete (m³) | 720 | 580 | In Stock | 4535200% | 125 | CementEx Ltd | Foundation | Quality approved
PRJ002 | Materials | Rebar (tonnes) | 320 | 240 | In Stock | 4535200% | 980 | SteelCorp UK | Structure | Grade 60
PRJ002 | Safety Equipment | Fall Protection | 70 | 65 | Active | 4534700% | 180 | SafetyFirst Ltd | All Zones | New equipment
PRJ003 | Skilled Labor | Concrete Workers | 18 | 15 | Active | 4533200% | 280 | StaffPro Ltd | Foundation | Need more workers
PRJ003 | Skilled Labor | Steel Fixers | 10 | 9 | Active | 4533200% | 295 | MetalPro Ltd | Structure | On schedule
PRJ003 | Skilled Labor | MEP Technicians | 8 | 7 | Active | 4534200% | 310 | TechStaff UK | MEP | Specialized team
PRJ003 | Equipment | Tower Crane | 1 | 1 | Operational | 4533200% | 8500 | CranePro UK | Structure | New installation
PRJ003 | Equipment | Concrete Pumps | 2 | 1 | Maintenance | 4533200% | 2200 | PumpMaster Ltd | Foundation | One under repair
PRJ003 | Materials | Concrete (m³) | 650 | 480 | In Stock | 4534200% | 125 | CementEx Ltd | Foundation | Regular supply
PRJ003 | Materials | Rebar (tonnes) | 280 | 190 | In Stock | 4534200% | 980 | SteelCorp UK | Structure | Grade 60
PRJ003 | Safety Equipment | Fall Protection | 60 | 55 | Active | 4533200% | 180 | SafetyFirst Ltd | All Zones | Monthly inspection
PRJ004 | Skilled Labor | Concrete Workers | 22 | 20 | Active | 4529600% | 280 | StaffPro Ltd | Foundation | High efficiency
PRJ004 | Skilled Labor | Steel Fixers | 14 | 12 | Active | 4529600% | 295 | MetalPro Ltd | Structure | Two on leave
PRJ004 | Skilled Labor | MEP Technicians | 10 | 9 | Active | 4530600% | 310 | TechStaff UK | MEP | Specialized work
PRJ004 | Equipment | Tower Crane | 2 | 1 | Maintenance | 4529600% | 8500 | CranePro UK | Structure | One for repair
PRJ004 | Equipment | Concrete Pumps | 3 | 2 | Operational | 4529600% | 2200 | PumpMaster Ltd | Foundation | Regular service
PRJ004 | Materials | Concrete (m³) | 780 | 650 | In Stock | 4530600% | 125 | CementEx Ltd | Foundation | Quality tested
PRJ004 | Materials | Rebar (tonnes) | 340 | 280 | In Stock | 4530600% | 980 | SteelCorp UK | Structure | Grade 60
PRJ004 | Safety Equipment | Fall Protection | 75 | 70 | Active | 4529600% | 180 | SafetyFirst Ltd | All Zones | Recently inspected
PRJ005 | Skilled Labor | Concrete Workers | 30 | 28 | Active | 4534200% | 280 | StaffPro Ltd | Foundation | Additional hired
PRJ005 | Skilled Labor | Steel Fixers | 18 | 16 | Active | 4534200% | 295 | MetalPro Ltd | Structure | Good performance
PRJ005 | Skilled Labor | MEP Technicians | 14 | 12 | Active | 4535200% | 310 | TechStaff UK | MEP | Specialized team
PRJ005 | Equipment | Tower Crane | 2 | 2 | Operational | 4534200% | 8500 | CranePro UK | Structure | Full utilization
PRJ005 | Equipment | Concrete Pumps | 4 | 3 | Operational | 4534200% | 2200 | PumpMaster Ltd | Foundation | One standby
PRJ005 | Materials | Concrete (m³) | 920 | 780 | In Stock | 4535200% | 125 | CementEx Ltd | Foundation | Large order
PRJ005 | Materials | Rebar (tonnes) | 420 | 350 | In Stock | 4535200% | 980 | SteelCorp UK | Structure | Grade 60
PRJ005 | Safety Equipment | Fall Protection | 95 | 88 | Active | 4534200% | 180 | SafetyFirst Ltd | All Zones | New equipment

## Floors_Progress (hidden)
Project_ID | Floor_Num | Status | completion_pct | last_updated | inspection_status | delay_reason | quality_rating | responsible_team | next_milestone
PRJ001 | B2 | Completed | 1 | 15/1/2024 | Passed | None | A | Foundation Team | None
PRJ001 | B1 | Completed | 1 | 1/2/2024 | Passed | None | A | Foundation Team | None
PRJ001 | 1 | Completed | 1 | 20/2/2024 | Passed | None | A | Structure Team | None
PRJ001 | 2 | Completed | 1 | 5/3/2024 | Passed | None | A | Structure Team | None
PRJ001 | 3 | In Progress | 0.85 | 18/3/2024 | Pending | Material Delay | Pending | Structure Team | Steel Fixing
PRJ001 | 4 | In Progress | 0.6 | 18/3/2024 | Pending | None | Pending | Structure Team | Concrete Pour
PRJ001 | 5 | In Progress | 0.3 | 18/3/2024 | Not Started | None | Pending | Structure Team | Formwork
PRJ001 | 6 | Not Started | 0 | N/A | Not Started | Not Started | Pending | Structure Team | Layout
PRJ002 | B2 | Completed | 1 | 1/2/2024 | Passed | None | A | Foundation Team | None
PRJ002 | B1 | Completed | 1 | 15/2/2024 | Passed | None | A | Foundation Team | None
PRJ002 | 1 | Completed | 1 | 1/3/2024 | Passed | None | A | Structure Team | None
PRJ002 | 2 | In Progress | 0.9 | 18/3/2024 | Pending | Weather | Pending | Structure Team | Final Inspection
PRJ002 | 3 | In Progress | 0.65 | 18/3/2024 | Pending | None | Pending | Structure Team | MEP Installation
PRJ002 | 4 | In Progress | 0.35 | 18/3/2024 | Not Started | None | Pending | Structure Team | Steel Fixing
PRJ002 | 5 | Not Started | 0 | N/A | Not Started | Not Started | Pending | Structure Team | Layout
PRJ003 | B1 | Completed | 1 | 25/2/2024 | Passed | None | A | Foundation Team | None
PRJ003 | 1 | Completed | 1 | 10/3/2024 | Passed | None | A | Structure Team | None
PRJ003 | 2 | In Progress | 0.8 | 18/3/2024 | Pending | Labor Shortage | Pending | Structure Team | MEP Installation
PRJ003 | 3 | In Progress | 0.45 | 18/3/2024 | Not Started | None | Pending | Structure Team | Concrete Pour
PRJ003 | 4 | Not Started | 0 | N/A | Not Started | Not Started | Pending | Structure Team | Layout
PRJ004 | B2 | Completed | 1 | 1/2/2024 | Passed | None | A | Foundation Team | None
PRJ004 | B1 | Completed | 1 | 15/2/2024 | Passed | None | A | Foundation Team | None
PRJ004 | 1 | Completed | 1 | 1/3/2024 | Passed | None | A | Structure Team | None
PRJ004 | 2 | Completed | 1 | 15/3/2024 | Passed | None | A | Structure Team | None
PRJ004 | 3 | In Progress | 0.75 | 18/3/2024 | Pending | Equipment Failure | Pending | Structure Team | MEP Installation
PRJ004 | 4 | In Progress | 0.4 | 18/3/2024 | Not Started | None | Pending | Structure Team | Steel Fixing
PRJ004 | 5 | Not Started | 0 | N/A | Not Started | Not Started | Pending | Structure Team | Layout
PRJ005 | B3 | Completed | 1 | 1/2/2024 | Passed | None | A | Foundation Team | None
PRJ005 | B2 | Completed | 1 | 15/2/2024 | Passed | None | A | Foundation Team | None
PRJ005 | B1 | Completed | 1 | 1/3/2024 | Passed | None | A | Foundation Team | None
PRJ005 | 1 | Completed | 1 | 15/3/2024 | Passed | None | A | Structure Team | None
PRJ005 | 2 | In Progress | 0.7 | 18/3/2024 | Pending | Material Delay | Pending | Structure Team | MEP Installation
PRJ005 | 3 | In Progress | 0.35 | 18/3/2024 | Not Started | None | Pending | Structure Team | Concrete Pour
PRJ005 | 4 | Not Started | 0 | N/A | Not Started | Not Started | Pending | Structure Team | Layout

## Project_Timeline_Floors_Progres
Project_ID | Building_Name | Start_Date | Planned_End_Date | Current_Status | Floor_Count | Location | Floor_Num | Status | completion_pct | delay_reason | Days_Elapsed
PRJ001 | Azure Heights Tower | 4530600% | 4583800% | In Progress | 32 | London | B2 | Completed | 1 | None | 402
PRJ001 | Azure Heights Tower | 4530600% | 4583800% | In Progress | 32 | London | B1 | Completed | 1 | None | 402
PRJ001 | Azure Heights Tower | 4530600% | 4583800% | In Progress | 32 | London | 1 | Completed | 1 | None | 402
PRJ001 | Azure Heights Tower | 4530600% | 4583800% | In Progress | 32 | London | 2 | Completed | 1 | None | 402
PRJ001 | Azure Heights Tower | 4530600% | 4583800% | In Progress | 32 | London | 3 | In Progress | 0.85 | Material Delay | 402
PRJ001 | Azure Heights Tower | 4530600% | 4583800% | In Progress | 32 | London | 4 | In Progress | 0.6 | None | 402
PRJ001 | Azure Heights Tower | 4530600% | 4583800% | In Progress | 32 | London | 5 | In Progress | 0.3 | None | 402
PRJ001 | Azure Heights Tower | 4530600% | 4583800% | In Progress | 32 | London | 6 | Not Started | 0 | Not Started | 402
PRJ002 | Emerald Business Plaza | 4535200% | 4600600% | In Progress | 28 | Manchester | B2 | Completed | 1 | None | 356
PRJ002 | Emerald Business Plaza | 4535200% | 4600600% | In Progress | 28 | Manchester | B1 | Completed | 1 | None | 356
PRJ002 | Emerald Business Plaza | 4535200% | 4600600% | In Progress | 28 | Manchester | 1 | Completed | 1 | None | 356
PRJ002 | Emerald Business Plaza | 4535200% | 4600600% | In Progress | 28 | Manchester | 2 | In Progress | 0.9 | Weather | 356
PRJ002 | Emerald Business Plaza | 4535200% | 4600600% | In Progress | 28 | Manchester | 3 | In Progress | 0.65 | None | 356
PRJ002 | Emerald Business Plaza | 4535200% | 4600600% | In Progress | 28 | Manchester | 4 | In Progress | 0.35 | None | 356
PRJ002 | Emerald Business Plaza | 4535200% | 4600600% | In Progress | 28 | Manchester | 5 | Not Started | 0 | Not Started | 356
PRJ003 | Sapphire Residences | 4533200% | 4588900% | In Progress | 25 | Birmingham | B1 | Completed | 1 | None | 376
PRJ003 | Sapphire Residences | 4533200% | 4588900% | In Progress | 25 | Birmingham | 1 | Completed | 1 | None | 376
PRJ003 | Sapphire Residences | 4533200% | 4588900% | In Progress | 25 | Birmingham | 2 | In Progress | 0.8 | Labor Shortage | 376
PRJ003 | Sapphire Residences | 4533200% | 4588900% | In Progress | 25 | Birmingham | 3 | In Progress | 0.45 | None | 376
PRJ003 | Sapphire Residences | 4533200% | 4588900% | In Progress | 25 | Birmingham | 4 | Not Started | 0 | Not Started | 376
PRJ004 | Crystal Garden Complex | 4529600% | 4586300% | In Progress | 30 | Leeds | B2 | Completed | 1 | None | 412
PRJ004 | Crystal Garden Complex | 4529600% | 4586300% | In Progress | 30 | Leeds | B1 | Completed | 1 | None | 412
PRJ004 | Crystal Garden Complex | 4529600% | 4586300% | In Progress | 30 | Leeds | 1 | Completed | 1 | None | 412
PRJ004 | Crystal Garden Complex | 4529600% | 4586300% | In Progress | 30 | Leeds | 2 | Completed | 1 | None | 412
PRJ004 | Crystal Garden Complex | 4529600% | 4586300% | In Progress | 30 | Leeds | 3 | In Progress | 0.75 | Equipment Failure | 412
PRJ004 | Crystal Garden Complex | 4529600% | 4586300% | In Progress | 30 | Leeds | 4 | In Progress | 0.4 | None | 412
PRJ004 | Crystal Garden Complex | 4529600% | 4586300% | In Progress | 30 | Leeds | 5 | Not Started | 0 | Not Started | 412
PRJ005 | Riverside Tower | 4534200% | 4591000% | In Progress | 35 | Liverpool | B3 | Completed | 1 | None | 366
PRJ005 | Riverside Tower | 4534200% | 4591000% | In Progress | 35 | Liverpool | B2 | Completed | 1 | None | 366
PRJ005 | Riverside Tower | 4534200% | 4591000% | In Progress | 35 | Liverpool | B1 | Completed | 1 | None | 366
PRJ005 | Riverside Tower | 4534200% | 4591000% | In Progress | 35 | Liverpool | 1 | Completed | 1 | None | 366
PRJ005 | Riverside Tower | 4534200% | 4591000% | In Progress | 35 | Liverpool | 2 | In Progress | 0.7 | Material Delay | 366
PRJ005 | Riverside Tower | 4534200% | 4591000% | In Progress | 35 | Liverpool | 3 | In Progress | 0.35 | None | 366
PRJ005 | Riverside Tower | 4534200% | 4591000% | In Progress | 35 | Liverpool | 4 | Not Started | 0 | Not Started | 366

## Consolidated Data
Project_ID | Building_Name | Start_Date | Planned_End_Date | Current_Status | Floor_Count | Overall Progress | Overall Cost Performance | original project duration | Days Elapsed | Overall completion percentage (Date)
PRJ001 | Azure Heights Tower | 4530600% | 4583800% | In Progress | 32 | 0.82143 | 0.9027 | 532 | 402 | 0.75564
PRJ002 | Emerald Business Plaza | 4535200% | 4600600% | In Progress | 28 | 0.81667 | 0.83495 | 654 | 356 | 0.54434
PRJ003 | Sapphire Residences | 4533200% | 4588900% | In Progress | 25 | 0.8125 | 0.79923 | 557 | 376 | 0.67504
PRJ004 | Crystal Garden Complex | 4529600% | 4586300% | In Progress | 30 | 0.85833 | 0.89841 | 567 | 412 | 0.72663
PRJ005 | Riverside Tower | 4534200% | 4591000% | In Progress | 35 | 0.84167 | 0.80054 | 568 | 366 | 0.64437
Row Labels | Sum of Days Elapsed | Sum of Overall completion percentage (Date)
Azure Heights Tower | 402 | 0.75564
Crystal Garden Complex | 412 | 0.72663
Emerald Business Plaza | 356 | 0.54434
Riverside Tower | 366 | 0.64437
Sapphire Residences | 376 | 0.67504
Grand Total | 1912 | 3.346

## Cost_Tracking4 (hidden)
Project_ID | cost_category | sub_category | budgeted_amount | actual_spent | invoice_date | payment_status | supplier_name | variance_pct | payment_due | notes
PRJ001 | Preliminaries | Site Setup | 450000 | 468000 | 15/1/2024 | Paid | SitePrep Ltd | 0.04 | Paid | Additional security requirements
PRJ001 | Preliminaries | Temporary Works | 280000 | 275000 | 20/1/2024 | Paid | TempWorks Co | -0.018 | Paid | Under budget
PRJ001 | Foundation | Excavation | 850000 | 842000 | 1/2/2024 | Paid | DigCo Ltd | -0.009 | Paid | Completed ahead of schedule
PRJ001 | Foundation | Piling | 1200000 | 1245000 | 15/2/2024 | Paid | PilePro UK | 0.038 | Paid | Additional piles required
PRJ001 | Foundation | Waterproofing | 380000 | 385000 | 20/2/2024 | Paid | WaterTech Ltd | 0.013 | Paid | Additional treatment needed
PRJ001 | Structure | Concrete Works | 2800000 | 2650000 | 1/3/2024 | In Process | ConcretePro Ltd | -0.054 | 30/3/2024 | Bulk purchase savings
PRJ001 | Structure | Steel Reinforcement | 1900000 | 2050000 | 5/3/2024 | In Process | SteelCorp UK | 0.079 | 4/4/2024 | Steel price increase
PRJ001 | Structure | Formwork | 950000 | 920000 | 10/3/2024 | In Process | FormTech Ltd | -0.032 | 9/4/2024 | Reuse of forms
PRJ001 | MEP | Electrical | 1850000 | 900000 | 15/3/2024 | In Process | ElectroPro Ltd | N/A | 14/4/2024 | Work in progress
PRJ001 | MEP | Plumbing | 1200000 | 580000 | 15/3/2024 | In Process | PlumbTech UK | N/A | 14/4/2024 | Work in progress
PRJ002 | Preliminaries | Site Setup | 380000 | 375000 | 20/2/2024 | Paid | SitePrep Ltd | -0.013 | Paid | Efficient setup
PRJ002 | Preliminaries | Temporary Works | 250000 | 248000 | 25/2/2024 | Paid | TempWorks Co | -0.008 | Paid | As planned
PRJ002 | Foundation | Excavation | 720000 | 735000 | 1/3/2024 | Paid | DigCo Ltd | 0.021 | Paid | Hard rock encountered
PRJ002 | Foundation | Piling | 980000 | 975000 | 5/3/2024 | Paid | PilePro UK | -0.005 | Paid | As per design
PRJ002 | Structure | Concrete Works | 2400000 | 1200000 | 15/3/2024 | In Process | ConcretePro Ltd | N/A | 14/4/2024 | Work in progress
PRJ002 | Structure | Steel Reinforcement | 1650000 | 850000 | 15/3/2024 | In Process | SteelCorp UK | N/A | 14/4/2024 | Work in progress
PRJ003 | Preliminaries | Site Setup | 320000 | 315000 | 15/2/2024 | Paid | SitePrep Ltd | -0.016 | Paid | Standard setup
PRJ003 | Foundation | Excavation | 580000 | 595000 | 25/2/2024 | Paid | DigCo Ltd | 0.026 | Paid | Additional depth required
PRJ003 | Foundation | Piling | 850000 | 848000 | 5/3/2024 | Paid | PilePro UK | -0.002 | Paid | As designed
PRJ003 | Structure | Concrete Works | 1950000 | 980000 | 15/3/2024 | In Process | ConcretePro Ltd | N/A | 14/4/2024 | Work in progress
PRJ003 | Structure | Steel Reinforcement | 1400000 | 680000 | 15/3/2024 | In Process | SteelCorp UK | N/A | 14/4/2024 | Work in progress
PRJ004 | Preliminaries | Site Setup | 420000 | 425000 | 10/1/2024 | Paid | SitePrep Ltd | 0.012 | Paid | Additional hoarding required
PRJ004 | Preliminaries | Temporary Works | 265000 | 268000 | 15/1/2024 | Paid | TempWorks Co | 0.011 | Paid | Additional temporary support
PRJ004 | Foundation | Excavation | 780000 | 775000 | 1/2/2024 | Paid | DigCo Ltd | -0.006 | Paid | Good ground conditions
PRJ004 | Foundation | Piling | 1100000 | 1095000 | 15/2/2024 | Paid | PilePro UK | -0.005 | Paid | As designed
PRJ004 | Structure | Concrete Works | 2600000 | 1850000 | 15/3/2024 | In Process | ConcretePro Ltd | N/A | 14/4/2024 | Work in progress
PRJ004 | Structure | Steel Reinforcement | 1800000 | 1200000 | 15/3/2024 | In Process | SteelCorp UK | N/A | 14/4/2024 | Work in progress
PRJ005 | Preliminaries | Site Setup | 480000 | 495000 | 25/2/2024 | Paid | SitePrep Ltd | 0.031 | Paid | Site access modifications
PRJ005 | Preliminaries | Temporary Works | 310000 | 308000 | 1/3/2024 | Paid | TempWorks Co | -0.006 | Paid | As planned
PRJ005 | Foundation | Excavation | 920000 | 945000 | 5/3/2024 | Paid | DigCo Ltd | 0.027 | Paid | Underground utilities diversion
PRJ005 | Foundation | Piling | 1350000 | 1320000 | 10/3/2024 | Paid | PilePro UK | -0.022 | Paid | Optimization in pile design
PRJ005 | Structure | Concrete Works | 3100000 | 1200000 | 15/3/2024 | In Process | ConcretePro Ltd | N/A | 14/4/2024 | Work in progress
PRJ005 | Structure | Steel Reinforcement | 2200000 | 850000 | 15/3/2024 | In Process | SteelCorp UK | N/A | 14/4/2024 | Work in progress

## Projects_Timeline3 (hidden)
Project_ID | Building_Name | Start_Date | Planned_End_Date | Current_Status | Floor_Count | Location
PRJ001 | Azure Heights Tower | 15/01/2024 | 30/06/2025 | In Progress | 32 | London
PRJ002 | Emerald Business Plaza | 01/03/2024 | 15/12/2025 | In Progress | 28 | Manchester
PRJ003 | Sapphire Residences | 10/02/2024 | 20/08/2025 | In Progress | 25 | Birmingham
PRJ004 | Crystal Garden Complex | 05/01/2024 | 25/07/2025 | In Progress | 30 | Leeds
PRJ005 | Riverside Tower | 20/02/2024 | 10/09/2025 | In Progress | 35 | Liverpool

## Project_Resources2 (hidden)
Project_ID | resource_type | resource_category | allocated_qty | utilized_qty | resource_status | allocation_date | unit_cost | supplier | location_zone | remarks
PRJ001 | Skilled Labor | Concrete Workers | 25 | 22 | Active | 1/2/2024 | 280 | StaffPro Ltd | Foundation | High performance team
PRJ001 | Skilled Labor | Steel Fixers | 15 | 15 | Active | 1/2/2024 | 295 | StaffPro Ltd | Structure | Full capacity utilization
PRJ001 | Skilled Labor | MEP Technicians | 12 | 10 | Active | 15/2/2024 | 310 | TechStaff UK | MEP | 2 on leave
PRJ001 | Skilled Labor | Carpenters | 18 | 15 | Active | 20/2/2024 | 275 | BuildStaff Co | Finishing | Training new staff
PRJ001 | Unskilled Labor | General Workers | 40 | 35 | Active | 1/2/2024 | 180 | WorkForce Inc | All Zones | Regular rotation
PRJ001 | Equipment | Tower Crane | 2 | 2 | Operational | 1/2/2024 | 8500 | CranePro UK | Structure | Monthly maintenance done
PRJ001 | Equipment | Concrete Pumps | 3 | 2 | Operational | 1/2/2024 | 2200 | PumpMaster Ltd | Foundation | One under repair
PRJ001 | Equipment | Excavators | 4 | 3 | Maintenance | 1/2/2024 | 1800 | EarthMovers Ltd | Foundation | Scheduled maintenance
PRJ001 | Equipment | Scaffolding Sets | 15 | 12 | Active | 15/2/2024 | 450 | ScaffoldPro | Structure | Safety checked
PRJ001 | Materials | Concrete (m³) | 850 | 720 | In Stock | 15/2/2024 | 125 | CementEx Ltd | Foundation | Quality tested
PRJ001 | Materials | Rebar (tonnes) | 380 | 290 | In Stock | 15/2/2024 | 980 | SteelCorp UK | Structure | Grade 60
PRJ001 | Safety Equipment | Fall Protection | 85 | 75 | Active | 1/2/2024 | 180 | SafetyFirst Ltd | All Zones | Monthly inspection done
PRJ001 | Special Equipment | BIM Scanner | 1 | 1 | Active | 10/3/2024 | 5500 | TechScan Ltd | All Zones | New equipment
PRJ002 | Skilled Labor | Concrete Workers | 20 | 18 | Active | 25/2/2024 | 280 | StaffPro Ltd | Foundation | Experienced team
PRJ002 | Skilled Labor | Steel Fixers | 12 | 12 | Active | 25/2/2024 | 295 | StaffPro Ltd | Structure | All present
PRJ002 | Skilled Labor | MEP Technicians | 10 | 8 | Active | 1/3/2024 | 310 | TechStaff UK | MEP | Short staffed
PRJ002 | Unskilled Labor | General Workers | 35 | 30 | Active | 25/2/2024 | 180 | WorkForce Inc | All Zones | Need more workers
PRJ002 | Equipment | Tower Crane | 1 | 1 | Operational | 25/2/2024 | 8500 | CranePro UK | Structure | Regular maintenance
PRJ002 | Equipment | Concrete Pumps | 2 | 2 | Operational | 25/2/2024 | 2200 | PumpMaster Ltd | Foundation | Working well
PRJ002 | Materials | Concrete (m³) | 720 | 580 | In Stock | 1/3/2024 | 125 | CementEx Ltd | Foundation | Quality approved
PRJ002 | Materials | Rebar (tonnes) | 320 | 240 | In Stock | 1/3/2024 | 980 | SteelCorp UK | Structure | Grade 60
PRJ002 | Safety Equipment | Fall Protection | 70 | 65 | Active | 25/2/2024 | 180 | SafetyFirst Ltd | All Zones | New equipment
PRJ003 | Skilled Labor | Concrete Workers | 18 | 15 | Active | 10/2/2024 | 280 | StaffPro Ltd | Foundation | Need more workers
PRJ003 | Skilled Labor | Steel Fixers | 10 | 9 | Active | 10/2/2024 | 295 | MetalPro Ltd | Structure | On schedule
PRJ003 | Skilled Labor | MEP Technicians | 8 | 7 | Active | 20/2/2024 | 310 | TechStaff UK | MEP | Specialized team
PRJ003 | Equipment | Tower Crane | 1 | 1 | Operational | 10/2/2024 | 8500 | CranePro UK | Structure | New installation
PRJ003 | Equipment | Concrete Pumps | 2 | 1 | Maintenance | 10/2/2024 | 2200 | PumpMaster Ltd | Foundation | One under repair
PRJ003 | Materials | Concrete (m³) | 650 | 480 | In Stock | 20/2/2024 | 125 | CementEx Ltd | Foundation | Regular supply
PRJ003 | Materials | Rebar (tonnes) | 280 | 190 | In Stock | 20/2/2024 | 980 | SteelCorp UK | Structure | Grade 60
PRJ003 | Safety Equipment | Fall Protection | 60 | 55 | Active | 10/2/2024 | 180 | SafetyFirst Ltd | All Zones | Monthly inspection
PRJ004 | Skilled Labor | Concrete Workers | 22 | 20 | Active | 5/1/2024 | 280 | StaffPro Ltd | Foundation | High efficiency
PRJ004 | Skilled Labor | Steel Fixers | 14 | 12 | Active | 5/1/2024 | 295 | MetalPro Ltd | Structure | Two on leave
PRJ004 | Skilled Labor | MEP Technicians | 10 | 9 | Active | 15/1/2024 | 310 | TechStaff UK | MEP | Specialized work
PRJ004 | Equipment | Tower Crane | 2 | 1 | Maintenance | 5/1/2024 | 8500 | CranePro UK | Structure | One for repair
PRJ004 | Equipment | Concrete Pumps | 3 | 2 | Operational | 5/1/2024 | 2200 | PumpMaster Ltd | Foundation | Regular service
PRJ004 | Materials | Concrete (m³) | 780 | 650 | In Stock | 15/1/2024 | 125 | CementEx Ltd | Foundation | Quality tested
PRJ004 | Materials | Rebar (tonnes) | 340 | 280 | In Stock | 15/1/2024 | 980 | SteelCorp UK | Structure | Grade 60
PRJ004 | Safety Equipment | Fall Protection | 75 | 70 | Active | 5/1/2024 | 180 | SafetyFirst Ltd | All Zones | Recently inspected
PRJ005 | Skilled Labor | Concrete Workers | 30 | 28 | Active | 20/2/2024 | 280 | StaffPro Ltd | Foundation | Additional hired
PRJ005 | Skilled Labor | Steel Fixers | 18 | 16 | Active | 20/2/2024 | 295 | MetalPro Ltd | Structure | Good performance
PRJ005 | Skilled Labor | MEP Technicians | 14 | 12 | Active | 1/3/2024 | 310 | TechStaff UK | MEP | Specialized team
PRJ005 | Equipment | Tower Crane | 2 | 2 | Operational | 20/2/2024 | 8500 | CranePro UK | Structure | Full utilization
PRJ005 | Equipment | Concrete Pumps | 4 | 3 | Operational | 20/2/2024 | 2200 | PumpMaster Ltd | Foundation | One standby
PRJ005 | Materials | Concrete (m³) | 920 | 780 | In Stock | 1/3/2024 | 125 | CementEx Ltd | Foundation | Large order
PRJ005 | Materials | Rebar (tonnes) | 420 | 350 | In Stock | 1/3/2024 | 980 | SteelCorp UK | Structure | Grade 60
PRJ005 | Safety Equipment | Fall Protection | 95 | 88 | Active | 20/2/2024 | 180 | SafetyFirst Ltd | All Zones | New equipment

## Floors_Progress1 (hidden)
Project_ID | Floor_Num | Status | completion_pct | last_updated | inspection_status | delay_reason | quality_rating | responsible_team | next_milestone
PRJ001 | B2 | Completed | 1 | 4530600% | Passed | None | A | Foundation Team | None
PRJ001 | B1 | Completed | 1 | 4532300% | Passed | None | A | Foundation Team | None
PRJ001 | 1 | Completed | 1 | 4534200% | Passed | None | A | Structure Team | None
PRJ001 | 2 | Completed | 1 | 4535600% | Passed | None | A | Structure Team | None
PRJ001 | 3 | In Progress | 0.85 | 4536900% | Pending | Material Delay | Pending | Structure Team | Steel Fixing
PRJ001 | 4 | In Progress | 0.6 | 4536900% | Pending | None | Pending | Structure Team | Concrete Pour
PRJ001 | 5 | In Progress | 0.3 | 4536900% | Not Started | None | Pending | Structure Team | Formwork
PRJ002 | B2 | Completed | 1 | 4532300% | Passed | None | A | Foundation Team | None
PRJ002 | B1 | Completed | 1 | 4533700% | Passed | None | A | Foundation Team | None
PRJ002 | 1 | Completed | 1 | 4535200% | Passed | None | A | Structure Team | None
PRJ002 | 2 | In Progress | 0.9 | 4536900% | Pending | Weather | Pending | Structure Team | Final Inspection
PRJ002 | 3 | In Progress | 0.65 | 4536900% | Pending | None | Pending | Structure Team | MEP Installation
PRJ002 | 4 | In Progress | 0.35 | 4536900% | Not Started | None | Pending | Structure Team | Steel Fixing
PRJ003 | B1 | Completed | 1 | 4534700% | Passed | None | A | Foundation Team | None
PRJ003 | 1 | Completed | 1 | 4536100% | Passed | None | A | Structure Team | None
PRJ003 | 2 | In Progress | 0.8 | 4536900% | Pending | Labor Shortage | Pending | Structure Team | MEP Installation
PRJ003 | 3 | In Progress | 0.45 | 4536900% | Not Started | None | Pending | Structure Team | Concrete Pour
PRJ004 | B2 | Completed | 1 | 4532300% | Passed | None | A | Foundation Team | None
PRJ004 | B1 | Completed | 1 | 4533700% | Passed | None | A | Foundation Team | None
PRJ004 | 1 | Completed | 1 | 4535200% | Passed | None | A | Structure Team | None
PRJ004 | 2 | Completed | 1 | 4536600% | Passed | None | A | Structure Team | None
PRJ004 | 3 | In Progress | 0.75 | 4536900% | Pending | Equipment Failure | Pending | Structure Team | MEP Installation
PRJ004 | 4 | In Progress | 0.4 | 4536900% | Not Started | None | Pending | Structure Team | Steel Fixing
PRJ005 | B3 | Completed | 1 | 4532300% | Passed | None | A | Foundation Team | None
PRJ005 | B2 | Completed | 1 | 4533700% | Passed | None | A | Foundation Team | None
PRJ005 | B1 | Completed | 1 | 4535200% | Passed | None | A | Foundation Team | None
PRJ005 | 1 | Completed | 1 | 4536600% | Passed | None | A | Structure Team | None
PRJ005 | 2 | In Progress | 0.7 | 4536900% | Pending | Material Delay | Pending | Structure Team | MEP Installation
PRJ005 | 3 | In Progress | 0.35 | 4536900% | Not Started | None | Pending | Structure Team | Concrete Pour

## Sheet1
Project_ID | Building_Name | Start_Date | Planned_End_Date | Current_Status | Floor_Count | Location |  |  |  |  | Challenge Requirements
PRJ001 | Azure Heights Tower | 15/01/2024 | 30/06/2025 | In Progress | 32 | London
PRJ002 | Emerald Business Plaza | 01/03/2024 | 15/12/2025 | In Progress | 28 | Manchester |  |  |  |  | Create a consolidated report using Power Query that shows:
PRJ003 | Sapphire Residences | 10/02/2024 | 20/08/2025 | In Progress | 25 | Birmingham
PRJ004 | Crystal Garden Complex | 05/01/2024 | 25/07/2025 | In Progress | 30 | Leeds |  |  |  |  | 1. Project overview with total floors completed (completion_pct = 100%)
PRJ005 | Riverside Tower | 20/02/2024 | 10/09/2025 | In Progress | 35 | Liverpool |  |  |  |  | 2. Current progress percentage per project (average of all floors)
3. Budget performance (variance between budgeted and actual costs)
Project_ID | Floor_Num | Status | completion_pct | last_updated | inspection_status | delay_reason | quality_rating | responsible_team | next_milestone |  | 4. Days elapsed since project start
PRJ001 | B2 | Completed | 100% | 15/1/2024 | Passed | None | A | Foundation Team | None |  | 5. Estimated completion rate (floors completed per month)
PRJ001 | B1 | Completed | 100% | 1/2/2024 | Passed | None | A | Foundation Team | None
PRJ001 | 1 | Completed | 100% | 20/2/2024 | Passed | None | A | Structure Team | None
PRJ001 | 2 | Completed | 100% | 5/3/2024 | Passed | None | A | Structure Team | None
PRJ001 | 3 | In Progress | 85% | 18/3/2024 | Pending | Material Delay | Pending | Structure Team | Steel Fixing
PRJ001 | 4 | In Progress | 60% | 18/3/2024 | Pending | None | Pending | Structure Team | Concrete Pour
PRJ001 | 5 | In Progress | 30% | 18/3/2024 | Not Started | None | Pending | Structure Team | Formwork
PRJ001 | 6 | Not Started | 0% | N/A | Not Started | Not Started | Pending | Structure Team | Layout
PRJ002 | B2 | Completed | 100% | 1/2/2024 | Passed | None | A | Foundation Team | None
PRJ002 | B1 | Completed | 100% | 15/2/2024 | Passed | None | A | Foundation Team | None
PRJ002 | 1 | Completed | 100% | 1/3/2024 | Passed | None | A | Structure Team | None
PRJ002 | 2 | In Progress | 90% | 18/3/2024 | Pending | Weather | Pending | Structure Team | Final Inspection
PRJ002 | 3 | In Progress | 65% | 18/3/2024 | Pending | None | Pending | Structure Team | MEP Installation
PRJ002 | 4 | In Progress | 35% | 18/3/2024 | Not Started | None | Pending | Structure Team | Steel Fixing
PRJ002 | 5 | Not Started | 0% | N/A | Not Started | Not Started | Pending | Structure Team | Layout
PRJ003 | B1 | Completed | 100% | 25/2/2024 | Passed | None | A | Foundation Team | None
PRJ003 | 1 | Completed | 100% | 10/3/2024 | Passed | None | A | Structure Team | None
PRJ003 | 2 | In Progress | 80% | 18/3/2024 | Pending | Labor Shortage | Pending | Structure Team | MEP Installation
PRJ003 | 3 | In Progress | 45% | 18/3/2024 | Not Started | None | Pending | Structure Team | Concrete Pour
PRJ003 | 4 | Not Started | 0% | N/A | Not Started | Not Started | Pending | Structure Team | Layout
PRJ004 | B2 | Completed | 100% | 1/2/2024 | Passed | None | A | Foundation Team | None
PRJ004 | B1 | Completed | 100% | 15/2/2024 | Passed | None | A | Foundation Team | None
PRJ004 | 1 | Completed | 100% | 1/3/2024 | Passed | None | A | Structure Team | None
PRJ004 | 2 | Completed | 100% | 15/3/2024 | Passed | None | A | Structure Team | None
PRJ004 | 3 | In Progress | 75% | 18/3/2024 | Pending | Equipment Failure | Pending | Structure Team | MEP Installation
PRJ004 | 4 | In Progress | 40% | 18/3/2024 | Not Started | None | Pending | Structure Team | Steel Fixing
PRJ004 | 5 | Not Started | 0% | N/A | Not Started | Not Started | Pending | Structure Team | Layout
PRJ005 | B3 | Completed | 100% | 1/2/2024 | Passed | None | A | Foundation Team | None
PRJ005 | B2 | Completed | 100% | 15/2/2024 | Passed | None | A | Foundation Team | None
PRJ005 | B1 | Completed | 100% | 1/3/2024 | Passed | None | A | Foundation Team | None
PRJ005 | 1 | Completed | 100% | 15/3/2024 | Passed | None | A | Structure Team | None
PRJ005 | 2 | In Progress | 70% | 18/3/2024 | Pending | Material Delay | Pending | Structure Team | MEP Installation
PRJ005 | 3 | In Progress | 35% | 18/3/2024 | Not Started | None | Pending | Structure Team | Concrete Pour
PRJ005 | 4 | Not Started | 0% | N/A | Not Started | Not Started | Pending | Structure Team | Layout
Project_ID | resource_type | resource_category | allocated_qty | utilized_qty | resource_status | allocation_date | unit_cost | supplier | location_zone | remarks
PRJ001 | Skilled Labor | Concrete Workers | 25 | 22 | Active | 1/2/2024 | 280 | StaffPro Ltd | Foundation | High performance team
PRJ001 | Skilled Labor | Steel Fixers | 15 | 15 | Active | 1/2/2024 | 295 | StaffPro Ltd | Structure | Full capacity utilization
PRJ001 | Skilled Labor | MEP Technicians | 12 | 10 | Active | 15/2/2024 | 310 | TechStaff UK | MEP | 2 on leave
PRJ001 | Skilled Labor | Carpenters | 18 | 15 | Active | 20/2/2024 | 275 | BuildStaff Co | Finishing | Training new staff
PRJ001 | Unskilled Labor | General Workers | 40 | 35 | Active | 1/2/2024 | 180 | WorkForce Inc | All Zones | Regular rotation
PRJ001 | Equipment | Tower Crane | 2 | 2 | Operational | 1/2/2024 | 8500 | CranePro UK | Structure | Monthly maintenance done
PRJ001 | Equipment | Concrete Pumps | 3 | 2 | Operational | 1/2/2024 | 2200 | PumpMaster Ltd | Foundation | One under repair
PRJ001 | Equipment | Excavators | 4 | 3 | Maintenance | 1/2/2024 | 1800 | EarthMovers Ltd | Foundation | Scheduled maintenance
PRJ001 | Equipment | Scaffolding Sets | 15 | 12 | Active | 15/2/2024 | 450 | ScaffoldPro | Structure | Safety checked
PRJ001 | Materials | Concrete (m³) | 850 | 720 | In Stock | 15/2/2024 | 125 | CementEx Ltd | Foundation | Quality tested
PRJ001 | Materials | Rebar (tonnes) | 380 | 290 | In Stock | 15/2/2024 | 980 | SteelCorp UK | Structure | Grade 60
PRJ001 | Safety Equipment | Fall Protection | 85 | 75 | Active | 1/2/2024 | 180 | SafetyFirst Ltd | All Zones | Monthly inspection done
PRJ001 | Special Equipment | BIM Scanner | 1 | 1 | Active | 10/3/2024 | 5500 | TechScan Ltd | All Zones | New equipment
PRJ002 | Skilled Labor | Concrete Workers | 20 | 18 | Active | 25/2/2024 | 280 | StaffPro Ltd | Foundation | Experienced team
PRJ002 | Skilled Labor | Steel Fixers | 12 | 12 | Active | 25/2/2024 | 295 | StaffPro Ltd | Structure | All present
PRJ002 | Skilled Labor | MEP Technicians | 10 | 8 | Active | 1/3/2024 | 310 | TechStaff UK | MEP | Short staffed
PRJ002 | Unskilled Labor | General Workers | 35 | 30 | Active | 25/2/2024 | 180 | WorkForce Inc | All Zones | Need more workers
PRJ002 | Equipment | Tower Crane | 1 | 1 | Operational | 25/2/2024 | 8500 | CranePro UK | Structure | Regular maintenance
PRJ002 | Equipment | Concrete Pumps | 2 | 2 | Operational | 25/2/2024 | 2200 | PumpMaster Ltd | Foundation | Working well
PRJ002 | Materials | Concrete (m³) | 720 | 580 | In Stock | 1/3/2024 | 125 | CementEx Ltd | Foundation | Quality approved
PRJ002 | Materials | Rebar (tonnes) | 320 | 240 | In Stock | 1/3/2024 | 980 | SteelCorp UK | Structure | Grade 60
PRJ002 | Safety Equipment | Fall Protection | 70 | 65 | Active | 25/2/2024 | 180 | SafetyFirst Ltd | All Zones | New equipment
PRJ003 | Skilled Labor | Concrete Workers | 18 | 15 | Active | 10/2/2024 | 280 | StaffPro Ltd | Foundation | Need more workers
PRJ003 | Skilled Labor | Steel Fixers | 10 | 9 | Active | 10/2/2024 | 295 | MetalPro Ltd | Structure | On schedule
PRJ003 | Skilled Labor | MEP Technicians | 8 | 7 | Active | 20/2/2024 | 310 | TechStaff UK | MEP | Specialized team
PRJ003 | Equipment | Tower Crane | 1 | 1 | Operational | 10/2/2024 | 8500 | CranePro UK | Structure | New installation
PRJ003 | Equipment | Concrete Pumps | 2 | 1 | Maintenance | 10/2/2024 | 2200 | PumpMaster Ltd | Foundation | One under repair
PRJ003 | Materials | Concrete (m³) | 650 | 480 | In Stock | 20/2/2024 | 125 | CementEx Ltd | Foundation | Regular supply
PRJ003 | Materials | Rebar (tonnes) | 280 | 190 | In Stock | 20/2/2024 | 980 | SteelCorp UK | Structure | Grade 60
PRJ003 | Safety Equipment | Fall Protection | 60 | 55 | Active | 10/2/2024 | 180 | SafetyFirst Ltd | All Zones | Monthly inspection
PRJ004 | Skilled Labor | Concrete Workers | 22 | 20 | Active | 5/1/2024 | 280 | StaffPro Ltd | Foundation | High efficiency
PRJ004 | Skilled Labor | Steel Fixers | 14 | 12 | Active | 5/1/2024 | 295 | MetalPro Ltd | Structure | Two on leave
PRJ004 | Skilled Labor | MEP Technicians | 10 | 9 | Active | 15/1/2024 | 310 | TechStaff UK | MEP | Specialized work
PRJ004 | Equipment | Tower Crane | 2 | 1 | Maintenance | 5/1/2024 | 8500 | CranePro UK | Structure | One for repair
PRJ004 | Equipment | Concrete Pumps | 3 | 2 | Operational | 5/1/2024 | 2200 | PumpMaster Ltd | Foundation | Regular service
PRJ004 | Materials | Concrete (m³) | 780 | 650 | In Stock | 15/1/2024 | 125 | CementEx Ltd | Foundation | Quality tested
PRJ004 | Materials | Rebar (tonnes) | 340 | 280 | In Stock | 15/1/2024 | 980 | SteelCorp UK | Structure | Grade 60
PRJ004 | Safety Equipment | Fall Protection | 75 | 70 | Active | 5/1/2024 | 180 | SafetyFirst Ltd | All Zones | Recently inspected
PRJ005 | Skilled Labor | Concrete Workers | 30 | 28 | Active | 20/2/2024 | 280 | StaffPro Ltd | Foundation | Additional hired
PRJ005 | Skilled Labor | Steel Fixers | 18 | 16 | Active | 20/2/2024 | 295 | MetalPro Ltd | Structure | Good performance
PRJ005 | Skilled Labor | MEP Technicians | 14 | 12 | Active | 1/3/2024 | 310 | TechStaff UK | MEP | Specialized team
PRJ005 | Equipment | Tower Crane | 2 | 2 | Operational | 20/2/2024 | 8500 | CranePro UK | Structure | Full utilization
PRJ005 | Equipment | Concrete Pumps | 4 | 3 | Operational | 20/2/2024 | 2200 | PumpMaster Ltd | Foundation | One standby
PRJ005 | Materials | Concrete (m³) | 920 | 780 | In Stock | 1/3/2024 | 125 | CementEx Ltd | Foundation | Large order
PRJ005 | Materials | Rebar (tonnes) | 420 | 350 | In Stock | 1/3/2024 | 980 | SteelCorp UK | Structure | Grade 60
PRJ005 | Safety Equipment | Fall Protection | 95 | 88 | Active | 20/2/2024 | 180 | SafetyFirst Ltd | All Zones | New equipment
Project_ID | cost_category | sub_category | budgeted_amount | actual_spent | invoice_date | payment_status | supplier_name | variance_pct | payment_due | notes
PRJ001 | Preliminaries | Site Setup | 450000 | 468000 | 15/1/2024 | Paid | SitePrep Ltd | 4% | Paid | Additional security requirements
PRJ001 | Preliminaries | Temporary Works | 280000 | 275000 | 20/1/2024 | Paid | TempWorks Co | -1.8% | Paid | Under budget
PRJ001 | Foundation | Excavation | 850000 | 842000 | 1/2/2024 | Paid | DigCo Ltd | -0.9% | Paid | Completed ahead of schedule
PRJ001 | Foundation | Piling | 1200000 | 1245000 | 15/2/2024 | Paid | PilePro UK | 3.8% | Paid | Additional piles required
PRJ001 | Foundation | Waterproofing | 380000 | 385000 | 20/2/2024 | Paid | WaterTech Ltd | 1.3% | Paid | Additional treatment needed
PRJ001 | Structure | Concrete Works | 2800000 | 2650000 | 1/3/2024 | In Process | ConcretePro Ltd | -5.4% | 30/3/2024 | Bulk purchase savings
PRJ001 | Structure | Steel Reinforcement | 1900000 | 2050000 | 5/3/2024 | In Process | SteelCorp UK | 7.9% | 4/4/2024 | Steel price increase
PRJ001 | Structure | Formwork | 950000 | 920000 | 10/3/2024 | In Process | FormTech Ltd | -3.2% | 9/4/2024 | Reuse of forms
PRJ001 | MEP | Electrical | 1850000 | 900000 | 15/3/2024 | In Process | ElectroPro Ltd | N/A | 14/4/2024 | Work in progress
PRJ001 | MEP | Plumbing | 1200000 | 580000 | 15/3/2024 | In Process | PlumbTech UK | N/A | 14/4/2024 | Work in progress
PRJ002 | Preliminaries | Site Setup | 380000 | 375000 | 20/2/2024 | Paid | SitePrep Ltd | -1.3% | Paid | Efficient setup
PRJ002 | Preliminaries | Temporary Works | 250000 | 248000 | 25/2/2024 | Paid | TempWorks Co | -0.8% | Paid | As planned
PRJ002 | Foundation | Excavation | 720000 | 735000 | 1/3/2024 | Paid | DigCo Ltd | 2.1% | Paid | Hard rock encountered
PRJ002 | Foundation | Piling | 980000 | 975000 | 5/3/2024 | Paid | PilePro UK | -0.5% | Paid | As per design
PRJ002 | Structure | Concrete Works | 2400000 | 1200000 | 15/3/2024 | In Process | ConcretePro Ltd | N/A | 14/4/2024 | Work in progress
PRJ002 | Structure | Steel Reinforcement | 1650000 | 850000 | 15/3/2024 | In Process | SteelCorp UK | N/A | 14/4/2024 | Work in progress
PRJ003 | Preliminaries | Site Setup | 320000 | 315000 | 15/2/2024 | Paid | SitePrep Ltd | -1.6% | Paid | Standard setup
PRJ003 | Foundation | Excavation | 580000 | 595000 | 25/2/2024 | Paid | DigCo Ltd | 2.6% | Paid | Additional depth required
PRJ003 | Foundation | Piling | 850000 | 848000 | 5/3/2024 | Paid | PilePro UK | -0.2% | Paid | As designed
PRJ003 | Structure | Concrete Works | 1950000 | 980000 | 15/3/2024 | In Process | ConcretePro Ltd | N/A | 14/4/2024 | Work in progress
PRJ003 | Structure | Steel Reinforcement | 1400000 | 680000 | 15/3/2024 | In Process | SteelCorp UK | N/A | 14/4/2024 | Work in progress
PRJ004 | Preliminaries | Site Setup | 420000 | 425000 | 10/1/2024 | Paid | SitePrep Ltd | 1.2% | Paid | Additional hoarding required
PRJ004 | Preliminaries | Temporary Works | 265000 | 268000 | 15/1/2024 | Paid | TempWorks Co | 1.1% | Paid | Additional temporary support
PRJ004 | Foundation | Excavation | 780000 | 775000 | 1/2/2024 | Paid | DigCo Ltd | -0.6% | Paid | Good ground conditions
PRJ004 | Foundation | Piling | 1100000 | 1095000 | 15/2/2024 | Paid | PilePro UK | -0.5% | Paid | As designed
PRJ004 | Structure | Concrete Works | 2600000 | 1850000 | 15/3/2024 | In Process | ConcretePro Ltd | N/A | 14/4/2024 | Work in progress
PRJ004 | Structure | Steel Reinforcement | 1800000 | 1200000 | 15/3/2024 | In Process | SteelCorp UK | N/A | 14/4/2024 | Work in progress
PRJ005 | Preliminaries | Site Setup | 480000 | 495000 | 25/2/2024 | Paid | SitePrep Ltd | 3.1% | Paid | Site access modifications
PRJ005 | Preliminaries | Temporary Works | 310000 | 308000 | 1/3/2024 | Paid | TempWorks Co | -0.6% | Paid | As planned
PRJ005 | Foundation | Excavation | 920000 | 945000 | 5/3/2024 | Paid | DigCo Ltd | 2.7% | Paid | Underground utilities diversion
PRJ005 | Foundation | Piling | 1350000 | 1320000 | 10/3/2024 | Paid | PilePro UK | -2.2% | Paid | Optimization in pile design
PRJ005 | Structure | Concrete Works | 3100000 | 1200000 | 15/3/2024 | In Process | ConcretePro Ltd | N/A | 14/4/2024 | Work in progress
PRJ005 | Structure | Steel Reinforcement | 2200000 | 850000 | 15/3/2024 | In Process | SteelCorp UK | N/A | 14/4/2024 | Work in progress